## Sheet1
INSPECTION RECORD CHECK |  |  |  | request date | inspection date |  |  |  | remarks
10/28/22 in email titled Weekly Update sent by Tayor Smith, he states, “I think we will have a great idea on timeline of inspections by about midweek next week. Plumbing will take a bit longer than anticipated but they are going to hit it hard next week”
03/03/23 Taylor Smith emailed a weekly update that “Electrical continued, and they are getting really close. HVAC and Plumbing are in line for next week. James and I spoke with both of them yesterday and will be good to go … All that to say, I am pushing as hard as I can over these next two weeks to get inspections on the books.”
Plumbing | Plumbing | WALLY OVERMAN PLUMBING, INC | Underground | 2022-03-07 | 2022-03-07 | Active | Yes | Austin Bowman | no remarks
03/10/23 Taylor Smith emailed subject Weekly Update to Mattern with cc to Jim Wolfe, “I think we are almost in the homestretch of inspections!” and on the Weekly Update it states under Scheduled for Next week “Electrical and plumbing and HVAC (HVAC should be wrapped up next week, plumbing may bleed into the following week)" In weekly report on 03/24/23 WH reported scheduled for next week “Electrical (likely need a walkthrough before they can wrap up completely just to make sure we are good to go)”
On 04/10/23 Taylor Smith emailed, “Hoping to have electrical taken care of this week inspection wise and the HVAC and plumbing scheduled…” Weekly Update dated 04/10/23 states scheduled for next week, “Plumbing and HVAC final wrap ups. First electrical inspection on Tuesday (hopefully the only one!). Electrical tends to be a bit of a pain, but will keep you all up to date on what they say and how it goes. Pushing to have remaining inspections completed or at least called in and scheduled by the end of the week” Weekly status report on 04/14/23 states under Accomplished This Week, “small framing needed to complete electrical was completed, inspection next week. HVAC walkthrough for completion, small supply lines need to be connected then inspection will be called in” and under scheduled for next week, “HVAC to be completed and called in (when we can connect the gas to the fireplace). Electrical rough in inspection to be called in”
Electrical | Electrical | Ave Integration | Underground | 2023-04-26 | 2023-04-26 | Active | Yes | Christopher Bumb | floor boxes and kitchen
Plumbing | Plumbing | WALLY OVERMAN PLUMBING, INC | Partial Rough | 2023-05-01 | 2023-05-01 | Active | Yes | Mathew Mena | All rough good except two shower pan tests need to be performed.
On 05/05/23 the Weekly Report stated under Accomplished This Week: “electrical wrapped and ready for inspection (need one wire pull but will have that done Monday.)” and “plumbing inspection passed.” And represented Scheduled for next week was “HVAC and electrical inspection” On 5/12/23 Weekly update represented that HVAC inspection would occur the following week
Mechanical | HVAC | Wades Heating & Cooling | Partial Rough | 2022-05-11 | 2022-05-11 | Active | Yes | Mark Forrest | gas test on line for range under slab ok
Electrical | Electrical | Ave Integration | Underground | 2022-05-13 | 2022-05-13 | Active | Yes | Christopher Bumb | 400 Amp Service kitchen island
Mechanical | HVAC | Wades Heating & Cooling | Partial Rough | 2023-05-31 | 2023-06-01 | Active | Yes | Mark Forrest | re-test for kitchen under slab gas line modifications
06/02/23 Email from Taylor Smith of Weekly Update states, “had a lot of momentum this week with backframing portion as well as electrical. Still waiting to hear on the inspection (talked to Chris briefly), early next week they will have that completed.” Under Accomplished in the weekly udate it states, “Electrical inspection called in” and scheduled for next week: “Electrical inspection if it is not signed off today. Remaining partial plumbing inspection. HVAC call in”
Electrical | Electrical | Ave Integration | Rough | 2023-06-07 | 2023-06-07 | Active | Yes | Blaine Dalton | Check receptacle spacing in nook area on 2nd floor on final. Check for dividers in boxes for low voltage on final. Was told by Josh under cabinet Receptacles are going in the kitchen as well as two pop up outlets. Sink is going in island that was not yet installed at time of inspection. Check outlet spacing in master bath as dual vanity sinks were not installed at time of inspection. Corrections were made during the time of rough inspection.
6/07/23 Mrs. Mattern texted Josh of Ave Electroncs to say "Congratulations on passing the electrical inspection at Mattern place!" to which AVE replied, "Yes! Thank you! Excited that it passed!"
Mechanical | HVAC | Wades Heating & Cooling | Partial Rough | 2023-06-09 | 2023-06-12 | Active | No | Mark Forrest | draft stop/fire block missing at duct floor/ceiling penetrations--gas test gauge reading 0 psi--access panels requires for fireplace flex connectors, cutoffs and control boards--nail plate required at bottom of drain line 1st floor laundry room--is kitchen hood to be installed?--
Building | Consultation | WOLFE CONSTRUCTION, INC | Miscellaneous | 2023-06-15 | 2023-06-15 | Active | Yes | Kirk Praster | Onsite with the contractor for a CONSULTATION INSPECTION ONLY REGARDING REQUIRED FIREBLOCKING AND DRAFTSTOPPPING PER THE NCRC. Framing repairs are in progress with work ongoing and all required fireblocking and draftstopping will be inspected by the BUILDING INSPECTOR AS REQUIRED PER THE NC RESIDENTIAL BUILDING CODE AT THE ROUGH/FRAMING INSPECTION.
Mechanical | HVAC | Wades Heating & Cooling | Rough | 2023-06-15 | 2023-06-16 | Active | Yes | Mark Forrest | no kitchen hood to be installed at this time
06/16/23 Taylor Smith emailed, “Productive week! Mechanical inspections passed!” and attached a weekly report that contained, “Mechanical inspection signed off” and in the weekly reportalso wrote as accomplished "Consultative framing inspection" and "HVAC work in prep for inspection"
Building | Insulation Spray Foam - no Roof Mods Done | WOLFE CONSTRUCTION, INC | Miscellaneous | 2023-06-20 | 2023-06-20 | Active | Yes | Kirk Praster | Contractor wanted to verify that it was ok to install spray foam insulation in the roof system/no modifications or alterations were done in the roof and it is existing from the original construction.
6/23/23 weekly update states under accomplished this week, "Fire blocking as called out by inspector - Walkthrough with building inspector for insulation approval"
Building | Building | WOLFE CONSTRUCTION, INC | Rough | 2023-06-27 | 2023-06-27 | Active | Yes | Christopher Jones | no remarks
Building | Spray Foam Paperwork | WOLFE CONSTRUCTION, INC | Insulation |  | 2023-06-27 | Active | Yes | Christopher Jones | spray foam paper work on file
06/30/23 Weekly Update by Taylor Smith states "Building and insulation inspection passed"
Plumbing | Plumbing | WALLY OVERMAN PLUMBING, INC | Partial Rough | 2023-06-30 | 2023-07-03 | Active | Yes | Mathew Mena | Verified presence of under slab p-trap to serve a first floor shower.
Plumbing | Plumbing | WALLY OVERMAN PLUMBING, INC | Rough | 2023-09-11 | 2023-09-11 | Active | Yes | Mathew Mena | Shower pans approved.
Building | Building | WOLFE CONSTRUCTION, INC | Miscellaneous | 2023-09-21 | 2023-09-22 | Active | No | Christopher Jones | fire places added, need mechanical permit...looked @ fireblocking between floors
Mechanical | Fireplaces | Fireplace Editions | Rough | 2023-10-16 | 2023-10-17 | Active | No | Christopher Williams | no one present
Mechanical | Fireplaces | Fireplace Editions | Miscellaneous | 2023-10-18 | 2023-10-19 | Active | No | Christopher Williams | per contact need to reschedule
Mechanical | Fireplaces | Fireplace Editions | Final | 2023-10-20 | 2023-10-23 | Active | No | Mark Forrest | rough inspection not performed, fireplaces framing and vent pipe covered up w/out inspection; 001-015 Covered up without Inspection
Mechanical | Fireplaces | Fireplace Editions | Rough | 2023-10-24 | 2023-10-24 | Active | No | Mark Forrest | pictures from contractor do not have clear views of dimensions for vent/fireplace rough framing, clearances, penetrations and connections, sheetrock sections will need to be removed for rough inspection
Mechanical | Fireplaces | Fireplace Editions | Miscellaneous | 2023-10-26 | 2023-10-27 | Active | Yes | Mark Forrest | fireplace consultation--rough inspection still required, see previous inspection notes
Mechanical | Fireplaces | Fireplace Editions | Rough | 2023-10-30 | 2023-10-30 | Active | No | Mark Forrest | 001-005 Corrections Not Completed 001-015 Covered up without Inspection
Mechanical | HVAC | Wades Heating & Cooling | Final | 2023-10-31 | 2023-10-31 | Active | Yes | Mark Forrest | existing underground/indoor gas piping not on this permit
Mechanical | Fireplaces | Fireplace Editions | Rough | 2023-10-31 | 2023-10-31 | Active | No | Mark Forrest | clearance instructions for all vent pipe used required on site--1st floor gas firebox framing required to be accessible for rough framing inspection 001-015 Covered up without Inspection, 001-024; Provide Manufacturer's Installation Instructions on Job Site
Mechanical | Fireplaces | Fireplace Editions | Rough | 2023-11-03 | 2023-11-03 | Active | Yes | Christopher Williams | Confirmed clearances and combustible air for the BR fireplace (sealed combustion with an optional power venter).
Mechanical | Broiler | Beaver Brothers | Partial Final | 2023-11-07 | 2023-11-07 | Active | Yes | Christopher Williams | Final pending 2 water piping connections (by plumbing contractor). Gas piping/connection by others already inspected.
Mechanical | Fireplaces | Fireplace Editions | Final | 2023-11-08 | 2023-11-08 | Active | Yes | Christopher Williams
Mechanical | Broiler | Beaver Brothers | Final |  | 2023-11-14 | Active | Yes | Mathew Mena | Water connections complete.
Plumbing | Plumbing | WALLY OVERMAN PLUMBING, INC | Final | 2023-11-14 | 2023-11-14 | Active | No | Mathew Mena | 001-010 Work Not Ready for Inspection
Electrical | Electrical | Ave Integration | Final | 2023-11-14 | 2023-11-15 | Active | No | Blaine Dalton | Inspection made on 2nd and 3rd floor. Complete reinspection when ready on first floor. 3rd floor fireplace receptacle in access hole from bathroom not installed (Wires unterminated in box). Label disconnects throughout the 3rd floor. --2nd Floor-- Receptacles set back more than 1/4" throughout receptacle faces are set behind the cover faceplate. Both panels need to be fully labeled throughout. Unable to determine if Bathroom Exhaust fan in shower was GFCI protected due to panel labels. Loose connections in right side panel. Label all disconnects throughout entire project. Unable to inspect HVAC equipment due to panel labeling. Seal raceways in outside panel. All Junction boxes throughout must be accessible. Work must be complete for next inspection all access panels installed and kitchen equipment to determine spacing and accessibility. All sinks must be installed before final inspection. Verify AFCI protection throughout when panel labels are finished. 001-045-001 It is required to schedule inspection when ready NC Admin Code 18 B, 030-006
Plumbing | Plumbing | WALLY OVERMAN PLUMBING, INC | Final* | 2023-11-15 | 2023-11-15 | Active | Yes | Randy Lovings | Two lavatories and soaker tub in master not installed at this time and capped off. One lavatory for second floor hall bath not installed and caped off. Permit to be obtained when installed.
Electrical | Electrical | Ave Integration | Final | 2023-11-16 | 2023-11-16 | Active | No | Blaine Dalton | Work still being done job is not ready for a final. Contractor stated that counter tops were not being installed in kitchen now to be considered a "Hallway" Open studs and open wires hanging out of walls. Reinspection fee added.
Building | Building | WOLFE CONSTRUCTION, INC | Final | 2023-11-17 | 2023-11-17 | Active | No | James Wolffe | no remarks
Electrical | Electrical | Ave Integration | Final | 2023-11-20 | 2023-11-21 | Active | No | Blaine Dalton
Building | Building | WOLFE CONSTRUCTION, INC | Final | 2023-11-22 | 2023-11-22 | Active | No | James Wolffe | Building OK. Smokes and CO's installed. Needs electrical final.
Electrical | Electrical | Ave Integration | Final | 2023-11-27 | 2023-11-29 | Active | No | Blaine Dalton | Corrections not made. 3rd Floor access panel unable to open no handle installed to remove to access outlet in wall. 2nd floor new issues created Sink in "Pottery room" receptacles within 6' of sink need to be GFCI protected. Sink still not installed in bathroom on right side bathroom. Low voltage must be fully installed throughout for next inspection. receptacles on second floor not secured to mounting surface. Door sensor low voltage cable not terminated. Two breakers installed and terminated in the right-side panel still not labeled. Inspection stopped on 1st floor due to Low voltage cable not being terminated throughout (wires hanging out of walls). Was told by contractor that no countertops were being installed in kitchen but low voltage cable for undercabinet lights is hanging out of the walls not terminated. Full reinspection of 1st floor and outdoor area around the dwelling will be required on the next inspection. Junction box under kitchen island is not fully accessible. Inspection was stopped due to work not being complete and not ready for a final inspection. Reinspection fee added. 030-001 Not in Compliance with NEC; Requirements for Electrical Installations; not in compliance with Article 110
Electrical | Electrical | Ave Integration | Final* | 2023-11-30 | 2023-11-30 | Active | Yes | Blaine Dalton | Corrections made all junction boxes / Outlets in wall are accessible throughout. Only Countertop installed during the time of inspection in kitchen is the Island. Was told by contractor all other countertops in kitchen were deleted and were not being installed. Receptacle spacing met in kitchen wall where countertops and cabinets were originally being installed. Corrections made during the time of inspection.
Building | Building | WOLFE CONSTRUCTION, INC | Final |  | 2023-11-30 | Active | Yes | James Wolffe | no remarks